## Sheet1
Task List |  | April 15 2017
# | Work Project Description | Volunteer Project Leader | Materials Required | Tools Required | Completion Milestones
1 | Bleacher mesh replacement |  | Mesh | Wrenches, side cutters, sockets | 2017-04-15
2 | Tire Barrier repairs |  | Heat Shrink | Scissors /Knife, Hot air gun | 2017-04-15
3 | Track Painting Touch up |  | Paint | Brushes / Rollers | May
4 | Vehicle regeneration |  | Gas | Wrenches Battery booster Air | 2017-04-15
5 | Quad Maintenance |  | Choke cable | Tool Kit | 2017-04-15
6 | Lawn Tractor regeneration |  | Gas | Tool Kit, Air inflator | 2017-04-15
7 | Track Sweep |  | Gas | Air generator , Brooms | 2017-04-15
8 | Track weed elimination |  | Round up | Back pack applicator / Gloves | 2017-04-15
9 | Tire Barrier Tumble weed |  |  | Gloves , Spade, Garbage bags | 2017-04-15
10 | Storm pond fencing/ Gate |  | Poles, Fencing, Staples | Hammer, Side Cutters, Gloves | 2017-04-15
11 | Fencing between new and Existing Paddock area |  | TBA | TBA | TBA
12 | Turn 13 Curb extension |  | Concrete, paint , cribbing wood | Shovel, asphalt cutter, water pails, floats and trowels, brush | May
13 | Track Patching |  | Track patch, Water | water pails, floats and trowels, brush | May/ June
14 | Seeding Paddock |  | Seed and Fertilizer | Spreader and soil turner | April/ May
15 | Parking ground marking rope |  | Marking pegs, Rope | Hammer, Tape measure | 2017-04-15
16 | Camera instalation Crows nest |  | Cameras Ethernet cable | Tool kit various items | 2017-04-15
17 | Crows nest siding |  | Siding (in Sea Can) | Tool kit various items (Platform hoist) | April/ May
18 | Crows Nest electric and lighting |  | Cable, outlets, light | Electrical trade | 2017-04-15
19 | Signs |  | Signage | Screws, Tool kit | 2017-04-15
20 | Replace swing barrier leg |  | New leg Internals | Small socket set | 2017-04-15
21 | Repair ATCO Doors and Frames |  | Wood casing | wood work kit | 2017-04-15
22 | Protect dry wall screws c can |  | Sealant | Grinder or hack saw | 2017-04-15
23 | Clean and lubricate locks |  | Cleaning agent , WD30 | Cleaning cloth , gloves , eye protection | 2017-04-15
24 | Dismantle Garbage enclosure |  |  | Gloves nail pulers prise bar, drill screw bits | 2017-04-15
25 | Build new Garbage enclosure Including internal man gate |  | Wood , posts , Screws Concrete | Barrow, water, shovel, saws screw drivers bits | 2017-04-15
26 | Rework fence at Main gate and pre grid areas where posts and fence need to meet |  | Staples , fencing | Wire cutters, hammer | 2017-04-15